## Sheet1
TAP Test Case
GitHub path | Test file | Test def |  | Test steps | Expected result | Result | Comment/Jira issue
DASHBOARD
test_api / dashboard | test_latest_events.py | DashboardLatestEvents | setUpClass | 1. Create test organization |  |  | DPNG-3365 Transfer submission fails with 500 Internal Server Error right after deployment
2. Produce an event in the tested organization - create a data set
3. Create another organization and create a data set in that organization
4. Retrieve latest events from dashboard
|  |  | test_10_latest_events_on_dashboard_the_same_as_in_LES | 1. Retrieve latest events from the LES, filtering with tested organization |  |  | DPNG-2091 There's no organisations distinction on dashboard in latest events section
2. Check that dashboard contains 10 latest events from LES
| test_metrics.py | Metrics | setUpClass | 1. Retrieve metrics for {}
|  |  | test_metrics_contains_all_keys | 1. Check that metrics response contains all expected fields
|  |  | test_service_count | 1. Get apps and services from cf and check that serviceUsage metrics is correct
|  |  | test_application_metrics | 1. Get apps from cf and check that appsRunning and appsDown metrics are correct
|  |  | test_user_count | 1. Get org users from cf and check that totalUsers metrics is correct
|  |  | test_data_metrics | 1. Get datasets and check datasetCount, privateDatasets, publicDatasets metrics are correct
DATA CATALOG
test_api / data_catalog | test_data_sets.py | GetDataSets | setUpClass | 1. Create test organization
2. Add admin to the organization
3. Create new transfer for each category
4. Ensure that transfers are finished
5. Get all data sets in the test organization
|  |  | test_match_dataset_to_transfer | 1. Check if a data set was created for each transfer
|  |  | test_get_datasets_by_category | 1. Retrieve datasets by categories
|  |  | test_get_datasets_by_creation_date | 1. Sort datasets by creation time and retrieve first two
2. Retrieve datasets for specified time range
|  |  | test_get_datasets_by_file_format | 1. Retrieve datasets by file format
|  |  | test_get_public_datasets_from_current_org | 1. Retrieve only public datasets
|  |  | test_get_private_datasets_from_current_org | 1. Retrieve only private datasets
|  |  | test_dataset_details | 1. Get transfer and matching dataset
2. Check that dataset exists for chosen transfer
3. Check dataset and transfer category
4. Check dataset and transfer org guid
5. Check dataset and transfer file format
6. Check dataset and transfer public status
7. Check dataset and transfer source uri
|  |  | test_get_data_sets_from_another_org | 1. Create another test organization
2. Retrieve public datasets from the new org
3. Check that no private data sets are visible in another org
4. Check that all public data sets are visible in another org
|  | UpdateDeleteDataSet | setUpClass | 1. Create test organization
2. Add admin to the organization
|  |  | _create_dataset | 1. Create new transfer
2. Wait for transfer to finish
3. Get data set matching to transfer
|  |  | _get_updated_dataset | 1. Wait for data set to update
|  |  | test_delete_dataset | 1. Delete the dataset
2. Get dataset list and check the deleted one is not on it
|  |  | test_cannot_delete_not_existing_dataset | 1. Delete dataset
2. Try to delete the dataset again
|  |  | test_change_private_dataset_to_public | 1. Update dataset from private to public
2. Check that private dataset was changed to public
|  |  | test_change_public_dataset_to_private | 1. Update dataset from public to private
2. Check that public dataset was changed to private
|  |  | test_update_dataset_category | 1. Update dataset, change category
2. Check if dataset category was changed
|  |  | test_cannot_update_dataset_to_incorrect_category | 1. Try to update a transfer with not existing category
| test_transfers.py | SubmitTransfer | setUpClass | 1. Create test organization
2. Add admin to the organization
|  |  | test_admin_can_get_transfer_list | 1. Check if the list of transfers can be retrieved
|  |  | test_submit_transfer | 1. Create new transfers and wait until the finish
2. Get transfers and check if they are the same as the uploaded ones
|  |  | test_no_token_in_create_transfer_response | 1. Create new transfer and check that 'token' field was not returned in response
|  |  | test_create_transfer_with_new_category | 1. Create a transfer with new category
2. Get transfer and check it's category
|  | TransferFromLocalFile | setUpClass | 1. Create test organization
2. Add admin to the organization
|  |  | test_create_transfer_from_file | 1. Generate sample csv file |  |  | DPNG-3156 DAS can't be found by uploader sometimes
2. Create transfer by uploading a csv file
3. Get data set matching to transfer {}
|  |  | test_submit_transfer_from_large_file | 1. Generate 20MB csv file
2. Create transfer by uploading the created file
3. Get data set matching to transfer {}
LATEST EVENTS SERVICE
test_api /latest_events_service | test_latest_events_service.py | LatestEventsService | test_latest_events | 1. Go to tab DataScience
2. Click tab: ATK or iPython or H2O or GearPump (for any application type that has instances)
3. For every type off application click hyperlink "Latest Events Dashboard"
4. Latest events for selected type of application are displayed
LATEST EVENTS SERVICE
test_api /platform_context | test_external_tools.py | TestExternalTools | test_check_status_code_of_external_tools | 1. Go to tab DataCatalog |  |  | DPNG-3366 Make Hue available from outside CF network
2. Gp to tab DataSets
3. Check availability of Arcadia/Hue
4. Select radiobox Arcadia/Hue by clicking radiobox near the name
5. Check status code displayed: 200 (OK)/4XX/5XX
SERVICES
test_api / services | test_marketplace.py | TestMarketplaceServices | setUpClass | 1. Create test organization and test space
2. Get list of available services from Marketplace
|  |  | test_check_marketplace_services_list_vs_cloudfoundry | 1. Check that services in cf are the same as in Marketplace
|  |  | test_create_gateway_instance | 1. Check that gateway service is available in Marketplace |  |  | DPNG-3177 Cannot create gateway instance - 502 Bad Gateway
2. Create instance of gateway ( plan). Check it exists
3. Delete the gateway instance and check it no longer exists
|  |  | test_create_zookeeper_instance | 1. Check that zookeper service is available in Marketplace |  |  | DPNG-2130 Cannot create zookeeper instance on Ireland - Bad Gateway
2. Create instance of zookeper ( plan). Check it exists
3. Delete the zookeper instance and check it no longer exists
|  |  | test_create_hbase_instance | 1. Check that hbase service is available in Marketplace |  |  | DPNG-2299 Error when creating hbase service instance in Marketplace
2. Create instance of hbase ( plan). Check it exists
3. Delete the hbase instance and check it no longer exists
|  |  | test_create_hdfs_instance | 1. Check that hdfs service is available in Marketplace |  |  | DPNG-3362 Creating hdfs instance returns 500 DPNG-2580 Creating instance of hdfs with plan encrypted fails with 502 Bad Gateway
2. Create instance of hdfs ( plan). Check it exists
3. Delete the hdfs instance and check it no longer exists
|  |  | test_create_memcached14_instance | 1. Check that memcached14 service is available in Marketplace |  |  | DPNG-2476 Cannot create memcached14 1Gb instance on Ireland - Bad Gateway
2. Create instance of memcached14 ( plan). Check it exists
3. Delete the memcached14 instance and check it no longer exists
|  |  | test_create_instance_of_other_services | 1. Check other services in Marketplace (excluding: atk, gateway, h2oUC, h2oUC-docker, hbase, hdfs, hello, simple-hello-env, zookeeper, pg-test-pz, hdfs-oauth, hdfs-alpha, memcached14)
2. Create other instance ( plan). Check it exists
3. Delete other instance and check it no longer exists
| test_instances.py | ServiceInstanceKeys | setUpClass | 1. Create test organization and test spaces
2. Get list of available services from Marketplace
|  |  | test_get_service_instance_summary_from_empty_space | 1. Create test instance in first space
2. Get service instances summary from second space
3. Check if service instance summary is empty in second space
|  |  | test_working_creation_service_instance_keys | 1. Create working test service instance ('zookeeper-wssb', 'kafka', 'smtp', 'cdh')
2. Check if created service instance exist in summary
3. Create key for created service instance and check its correctness
|  |  | test_failing_creation_service_instance_keys | 1. Create failing test service instance ('yarn', 'atk', 'hdfs', 'zookeeper', 'postgresql93', 'mysql56', 'redis28', 'mongodb26', 'couchdb16', 'neo4j21', 'arangodb22', 'rabbitmq33', 'memcached14', 'elasticsearch13', 'logstash14', 'nats', 'etcd', 'rethinkdb', 'influxdb088', 'mosquitto14', 'ipython', 'rstudio', 'hbase', 'gateway') |  |  | DPNG-3233 Creation of service keys for docker services does not work
2. Check if created service instance exist in summary
3. Create key for created service instance and check its correctness
USER_MANAGEMENT
test_api / user_management | test_onboarding.py | Onboarding | setUpClass | 1. Create organization
|  |  | test_simple_onboarding | 1. Send an invitation to a new user (login as tester-admin)
2. Verify email corectness: link pattern correctness, subject, content, sender.
3. Register new user after onboarding.
4. Check that the user and their organization exist
5. Check that user has got manager role.
|  |  | test_cannot_invite_existing_user.py | 1. Invite registered test user. |  |  | DPNG-2364 Onboarding existing user sends a new email invitation
2. Check that sending invitation to the same user causes an error.
|  |  | test_non_admin_user_cannot_invite_another_user | 1. Create a non-admin test user |  |  | DPNG-2366 Non admin user invites another user - http 500
2. Check an error is returned when non-admin tries to onboard another user
3. Check if non-admin user receiver 0 messages.
|  |  | test_cannot_create_an_account_with_invalid_code | 1. Check if an error is returned when user registers with invalid code
|  |  | test_cannot_use_the_same_activation_code_twice | 1. Invite a user
2. The new user registers using invitation code
3. Check that error is returned when the user tries to use code twice.
|  |  | test_invite_user_with_non_email_usernam | 1. Check that passing invalid email (eg. non_mail_username) results in error |  |  | DPNG-2625 Onboarding user with invalid e-mail as username results in Internal Server Error
|  |  | test_user_cannot_register_without_password | 1. Invite a new user |  |  | DPNG-2367 Registration without password - http 500
2. Check that an error is returned when the user tries to register without a password
3. Check that the user was not created
|  |  | test_user_cannot_register_already_existing_organization | 1. Invite a new user
2. Check that an error is returned when the user registers with an already-existing org name
3. Check that the user was not created
|  |  | test_user_cannot_register_with_no_organization_name | 1. Invite a new user |  |  | DPNG-2458 It's possible to create user without organization after onboarding
2. Check that an error is returned when user registers without passing an org name
3. Check that the user was not created
| test_org_users.py | AddExistingUserToOrganization | test_add_existing_user_with_no_roles | 1. Create an organization
2. Add a platform user to organization with no roles.
3. Check that user hasn't any roles.
|  |  | test_admin_adds_existing_user_one_role | 1. Create an organization.
2. Add a platform user to organization with one role: Org Manager, Auditor Manager, Billing Manager
3. Check that user has got role.
|  |  | test_admin_adds_existing_user_all_roles | 1. Create an organization.
2. Add a platform user to organization with all roles
3. Check that user has got all roles.
|  |  | test_admin_adds_user_which_is_already_in_org_with_the_same_role | 1. Create an organization.
2. Add a platform user to organization with roles
3. Add the same user to the same organization with the same roles
|  |  | test_admin_adds_user_which_is_already_in_org_with_different_role | 1. Create an organization.
2. Add a platform user to organization with roles: manager
3. Add the same user to the same organization with roles auditor
4. Check that user having sum of the roles.
|  |  | test_org_manager_adds_existing_user | 1. Create an organization.
2. Add a platform user as manager to the organization.
3. The new manager adds a platform user to the organization.
4. Check that ivited user has got expected roles.
|  |  | test_non_manager_cannot_add_existing_user_to_org | 1. Create an organization.
2. Add a platform user as non-manager to the organization. (with auditor role)
3. Check that the non-manager is not able to add a platform user to the org
|  |  | test_user_cannot_add_themselves_to_org | 1. Create an organization.
2. Check that a platform user (with auditor role) is not able to add themselves to the organization
|  |  | test_cannot_add_existing_user_to_non_existing_org | 1. Check that adding user to organization using invalid org guid (eg. this-org-guid-is-not-correct) raises an error
|  |  | test_cannot_add_existing_user_with_incorrect_role | 1. Create an organization.
2. Check that it is not possible to add user to the organization with incorrect role (eg. incorrect-role)
|  | AddNewUserToOrganization | test_add_new_user_with_no_roles | 1. Create an organization. |  |  | DPNG-2540 Cannot add new user to organization without roles
2. Create new user by adding to an organization with no roles
|  |  | test_admin_adds_new_user_one_role | 1. Create an organization. |  |  | DPNG-2181 Cannot add new organization user with role other than manager
2. Create new user by adding to an organization with roles: manager, auditor, billing manager
|  |  | test_admin_adds_new_user_all_roles | 1. Create an organization. |  |  | DPNG-2181 Cannot add new organization user with role other than manager
2. Create new user by adding to an organization with roles
|  |  | test_org_manager_adds_new_user | 1. Org manager adds a new user to an organization with roles: manager, auditor, billing manager |  |  | DPNG-2181 Cannot add new organization user with role other than manager
|  |  | test_non_manager_cannot_add_new_user_to_org | 1. Create new organization and add test user as non-manager role |  |  | DPNG-2271 /org/:org_guid/users returns different error messages for similar invalid requests
2. Create organization.
3. Add the user to organization.
4. Check that user cannot be added to organization by non-manager
|  |  | test_cannot_add_user_with_non_email_username | 1. Create an organization. |  |  | DPNG-2272 Attempt to add user with incorrect e-mail address results in Internal Server Error
2. Add user with non valid username to organization
3. Check that user with non valid username cannot be added to an organization
|  |  | test_cannot_add_new_user_to_non_existing_org | 1. Check that an error is raised when trying to add user using incorrect org guid
|  |  | test_cannot_add_new_user_incorrect_role | 1. Check that error is raised when trying to add user using incorrect roles
|  | UpdateOrganizationUser | test_update_org_user_add_new_role | 1. Create a test organization
2. Add test user to the organization with role: manager
3. Update user roles to roles: auditor
4. Check that roles were updated to: manager, auditor.
|  |  | test_update_org_user_remove_role | 1. Create a test organization
2. Add test user to the organization with roles: auditor
3. Update user roles to auditor.
4. Check that user has got auditor role.
|  |  | test_update_org_user_change_role | 1. Create a test organization
2. Add test user to the organization with roles: auditor.
3. Update user roles to: billing manager
4. Check that user has got billing manager role.
|  |  | test_update_org_user_with_the_same_role | 1. Create a test organization
2. Add test user to the organization with roles: auditor
3. Update user roles to the same roles
4. Check that user has got the same role.
|  |  | test_cannot_remove_manager_role_for_the_only_org_manager | 1. Create a test organization
2. Add test user to the organization as the only manager
3. Check that removing manager role of the only manager returns an error
|  |  | test_cannot_update_user_which_is_not_in_org | 1. Create test organization
2. Check that attempt to update a user via org they are not in returns an error
|  |  | test_user_cannot_update_user_in_org_where_they_are_not_added | 1. Create a test organization
2. Add updating user to the organization as: auditor
3. Add updated user to the organization as: auditor
4. Check that non-admin user cannot update another user in the test organization
|  |  | test_change_org_manager_role_in_org_with_two_managers | 1. Create a test organization
2. Add first manager to newly created organization
3. Add new manager to organization with a manager
4. Check that it's possible to remove manager role from the user
|  |  | test_cannot_update_non_existing_org_user | 1. Check that updating user which is not in an organization returns an error
|  |  | test_cannot_update_org_user_in_non_existing_org | 1. Check that updating user using invalid org guid returns an error
|  |  | test_cannot_update_org_user_with_incorrect_role | 1. Create a test organization
2. Add test user to organization with roles: billing_manager
3. Check that updating user using invalid role returns an error
|  |  | test_update_role_of_one_org_manager_cannot_update_second | 1. Create a test organization
2. Add two managers to the test organization
3. Remove manager role from one of the managers
4. Check that attempt to remove manager role from the second manager returns an error
|  |  | test_manager_can_update_user_role | 1. Create test org
2. Add org manager to organization
3. Add user to the test org with roles: manager, auditor, billing manager.
4. Org manager changes user role: manager, auditor, billing manager.
5. Check that user roles have been changed.
|  | Delete OrganizationUser | test_admin_deletes_the_only_org_user_non_manager | 1. Create a test organization
2. Add user to organization with non-manager role
3. Remove the user from the organization
|  |  | test_admin_cannot_delete_the_only_org_manager | 1. Create a test organization
2. Add user to organization as manager
3. Check that the only manager cannot be removed from the organization
|  |  | test_admin_deletes_one_of_org_users | 1. Create a test organization
2. Add two non-manager users to the organization
3. Remove one of the users from the organization
4. Check that user is not existing.
|  |  | test_admin_deletes_one_of_org_managers_cannot_delete_second | 1. Create a test organization
2. Add two managers to the organization
3. Remove one of the managers from the organization
4. Check that removing the last org manager returns an error
|  |  | test_admin_updates_role_of_one_org_manager_cannot_delete_second | 1. Create a test organization
2. Add two managers to the organization
3. Update roles of one of the managers to: non-manager
4. Check that last user has got manager role.
5. Check that removing the last manger returns an error
|  |  | test_admin_cannot_delete_org_user_twice | 1. Create a test organization |  |  | DPNG-2216 Deleting from org a user which is not in this org does not return any error
2. Add test user to organization
3. Delete test user from organization
4. Try to delete test user from organization second time
|  |  | test_admin_cannot_delete_non_existing_org_user | 1. Create a test organization |  |  | DPNG-2216 Deleting from org a user which is not in this org does not return any error
2. Check that an attempt to delete user which is not in org returns an error
|  |  | test_org_manager_can_delete_another_user | 1. Create a test organization |  |  | DPNG-2459 Cannot delete user - 404
2. Add org manager to organization
3. Add user to the test org with roles: manager, auditor, billing manager.
4. Org manager removes the user from the test org
5. Check that users were removed.
|  |  | test_non_manager_cannot_delete_user | 1. Create a test organization
2. Add deleting user to the organization with roles: non-manager roles
3. Add deleted user to the organization with deleted user roles.
4. Check that non-manager cannot delete user from org
|  | GetOrganizationUsers | setUpClass | 1. Create a test organization
2. Add new manager user to the test org
3. Add non-manager users to the test org
|  |  | test_non_manager_in_org_cannot_get_org_users | 1. Check that non-manager cannot get list of users in org
|  |  | test_manager_can_get_org_users | 1. Check that manager can get list of users in org
|  |  | test_user_not_in_org_cannot_get_org_users | 1. Create new org
2. Check that the user cannot get list of users in the test org
| test_organization.py | TestOrganization | test_create_organization | 1. Create an organization
2. Check that the organization is on the organization list
|  |  | test_rename_organization | 1. Create an organization
2. Update the organization, giving it new name
3. Check that the organization with new name is on the organization list
|  |  | test_delete_organization | 1. Create an organization
2. Check that the organization is on the org list
3. Delete the organization
4. Check that the organization is not on org list
|  |  | test_get_more_than_50_organizations | 1. Get list of organization and check how many there are
2. Add organizations, so that there are more than 50
3. Check that all new and old organizations are returned in org list
|  |  | test_delete_organization_with_user | 1. Create an organization
2. Add new platform user to the organization
3. Delete the organization
4. Check that the organization is not on org list
|  |  | test_create_the_same_organization | 1. Create an organization
2. Check that the organization is on the organization list
3. Create organization with the same name
4. Check that the same organization hasn't been created
test_api / user_management | test_space.py | Spaces | setUpClass | 1. Create an organization
|  |  | test_get_spaces_list_in_new_org | 1. Create new organization
2. Get list of spaces in the org and check that there are none
|  |  | test_create_space | 1. Create new space in the organization
2. Check that the space is on the org space list
|  |  | test_cannot_create_space_with_existing_name | 1. Create a space
2. Check that attempt to create a space with the same name in the same org returns an error
|  |  | test_create_space_with_long_nam | 1. Create space with name 400 char long
2. Check that the space with long name is present on space list
|  |  | test_create_space_with_empty_name | 1. Check that attempt to create space with empty name returns an error
|  |  | test_delete_space | 1. Create a space
2. Delete the space
3. Check that the deleted space is not present on the space list
|  |  | test_cannot_delete_not_existing_space | 1. Create a space
2. Delete the space
3. Check that attempt to delete the space again returns an error
|  |  | test_cannot_delete_space_with_user | 1. Create a space
2. Add new platform user to the space
3. Delete the space
4. Check that the space is not on the space list
test_api / user_management | test_space_users.py | GetSpaceUsers | setUpClass | 1. Create an organization
|  |  | test_get_user_list_from_deleted_space | 1. Delete the space from organization.
2. Check that retrieving list of users in the deleted space returns an error
|  | AddNewUserToSpace | test_add_non_existing_user_to_space | 1. Create new platform user with each role by adding him to space |  |  | DPNG-2287 Cannot register as a new user added to space
|  |  | test_cannot_add_new_user_with_no_roles | 1. Add new user with no roles.
|  |  | test_cannot_create_new_user_with_long_username | 1. Create new user with long username by adding him to space |  |  | DPNG-3363 Api email validation does not work properly
|  |  | test_cannot_create_new_user_with_non_email_username | 1. Create new user with non email username by adding him to space.
|  |  | test_cannot_create_user_with_existing_username | 1. Create user with existing username by adding him to space
|  |  | test_cannot_create_user_with_special_characters_username | 1. Create user with special characters username by adding him to space.
|  |  | test_cannot_create_user_with_non_ascii_characters_username | 1. Create user with special characters username (ąśćżźł) by adding him to space |  |  | DPNG-3583 Http 500 when email contains non ascii characters
|  |  | test_cannot_add_new_user_to_non_existing_space | 1. Create user by adding him to non-existing space: this-space-guid-is-not-correct
|  |  | test_cannot_add_new_user_with_incorrect_role | 1. Create user with incorrect role (i-don't-exist') .
|  | AddExistingUserToSpace | setUp | 1. Create test space
|  |  | test_add_existing_users_with_one_role | 1. Create new platform user by adding to the organization
2. Add user to space with role: Space Manager or Space Auditor or Space Developer
|  |  | test_add_existing_user_without_roles | 1. Check that attempt to add user to space with no roles returns an error |  |  | DPNG-2281 It's possible to add user to space without any roles using API
|  |  | test_add_existing_user_with_all_available_roles | 1. Add the user to space with all space roles.
|  |  | test_cannot_add_existing_user_to_non_existing_space | 1. Check that it is not possible to add existing user to space with invalid space role (incorrect-role)
|  | UpdateSpaceUser | setUp | 1. Create test space
|  |  | test_change_user_role | 1. Add user to space with role Space Manager.
2. Update the user, change their role to: Space Auditor.
3. Check that user has apropriate roles.
|  |  | test_cannot_change_role_to_invalid_one | 1. Add user to space with roleL Space Manager.
2. Check that updating space user roles to invalid ones returns an error.
|  |  | test_delete_user_roles_while_in_space | 1. Add user to space
2. Update the user, removing all space roles
3. Check that the user were removed from space.
4. Check that the user is still in the organization
|  |  | test_cannot_update_user_which_is_not_in_space | 1. Create test space
2. Check that attempt to update a user via space they are not in returns an error.
|  |  | test_cannot_update_non_existing_space_user | 1. Check that updating user which is not in space returns error
|  |  | test_cannot_update_space_user_in_not_existing_space | 1. Check that updating user using invalid space guid return an error
|  | DeleteSpaceUser | setUp | 1. Create test space
|  |  | test_delete_user_from_space | 1. Add the user to space
2. Delete the user from space
3. Check that the user is still in the organization
|  |  | test_delete_user_which_is_not_in_space | 1. Check that deleting the user from space they are not in returns an error |  |  | DPNG-2293 Deleting from space a user which is not in this space does not return any error
|  | SpaceUserPermissions | test_get_user_list | 1. Try to get user list from space by using every client type: "admin": True or "org_manager": True or "space_manager_in_org": True or "org_user": False or "other_org_manager": False or "other_user": False Check users priviliges.
|  |  | test_add_new_user | 1. Try to add new user with every client type. Check user priviliges.
|  |  | test_add_existing_user | 1. Try to add existing user to space with every client type. Check user priviliges.
|  |  | test_update_role_as_space_and_org_manager | 1. Create user (org manager, space manager in org) by adding him to space with role: Space Developer. |  |  | DPNG-3364 space and org managers can't change user space roles - http status 403
2. Update users space role on Space Auditor.
|  |  | test_update_role | 1. Try to change user space role using every client type: "admin": True, "org_user": False, "other_org_manager": False, "other_user": False Check user priviliges.
|  |  | test_delete_user | 1. Try to delete user from space using every client type. Check user priviliges.
|  |  | test_add_space | 1. Try to add new space using every client type: "admin": True, "org_manager": True, "space_manager_in_org": False, "org_user": False, "other_org_manager": False, "other_user": False Check user priviliges.
|  |  | test_delete_space | 1. Try to delete space using every client type: "admin": True, "org_manager": True, "space_manager_in_org": False, "org_user": False, "other_org_manager": False, "other_user": False
GUI_TESTS: LOGIN_PAGE
gui_tests/tests/login_page | LoginPageTest.spec.js |  | Login Page | 1. Get request to login page. | 1. Request status code should be successful (start with 2 or 3)
|  |  |  | 2. Log in with right username and password. | 2. User should be redirected to console.
|  |  |  | 3. Get request to dashboard page. | 3. Request status code should be successful (start with 2 or 3)
|  |  |  | 1. Log in with empty username or password. | 1. Information about incorrect username, password should be displayed.
|  |  |  | 1. Log in with wrong username or password. | 1. Information about incorrect username, password should be displayed.
GUI_TESTS: USER_MANAGEMENT
gui_tests/tests/user_management | OrganizationTest.spec.js |  | Manage Organizations | 1. Add new organization on submitting form. | 1. Successfull toast message should be displayed.
2. Organization should be on the list.
|  |  |  | 2. Add new space to organization. | 1. Successfull toast message should be displayed.
2. Space should be on the list.
| OrganizationUsersTest.spec.js |  | Manage Organization Users | 1. Add new user with role Org Auditor. | 1. Successfull toast message should be displayed.
2. User should be on the list.
|  |  |  | 2. Update user org role on Billing Manager. | 1. Successfull toast message should be displayed.
2. Check that user has roles: Org Auditor, Billing Manager.
|  |  |  | 3. Delete user. | 1. Successfull toast message should be displayed.
2. Check that user doesn't exist.
| DeleteOrganizationTest.spec.js |  | Manage Organizations | 1. Delete space. | 1. Successfull toast message should be displayed.
2. Check that space doesn't exist.
|  |  |  | 2. Delete organization. | 1. Successfull toast message should be displayed.
2. Check that organization doesn't exist.
GUI_TESTS: DATA_SCIENCE
Rstudio
gui_tests/tests/data_science/rstudio | RStudioInstanceTest.spec.js |  | Data Science -> Rstudio | 1. Check that title with organization name is displayed. | 1. Title with organization name should be displayed.
|  |  |  | 2. Create Rstudio instance. | 1. Successfull toast message should be displayed.
2. Rstudio instance should be on the list.
3. Hidden password should be displayed.
|  |  |  | 3. Click on: show App Password. | 1. Password should be displayed.
|  |  |  | 4. Click on instance App Url. | 1. User should be redirected to rstudio. |  | DPNG-3533 Bad Gateway error 502 after get request to Rstudio instance
2. User should be able to print hello world in rstudio shell.
|  |  |  | 5. Delete instance on clicking delete icon. | 1. Successfull toast message should be displayed.
2. Rstudio instance shouldn't exists on list of instances.